## Overview
Customer Success Portfolio Artifact — Lifecycle & Health Model
Quick Setup (blue cells are inputs)
Account Name | Acme Logistics | Health Score | Adoption % | Time-to-Value (days) | Risk Level
Industry | Logistics / Transportation
Customer Segment | Mid-Market
Start Date | 2025-11-27
CSM Owner | La Toya Caldwell
Renewal Date | 2026-11-27
Navigation
Account Profile | Go to Account Profile sheet
Onboarding Plan | Go to Onboarding Plan sheet
Success Plan | Go to Success Plan sheet
Health Model | Go to Health Model sheet
Exec Readout | Go to Exec Readout sheet
La Toya Caldwell ¦ Customer Success & Tech Strategy

## Account Profile
Account Profile
Account Summary
Account Name
Primary Contact | Jordan Lee
Title | VP Operations
Email | jordan.lee@acme.com
Customer Objective (1 sentence) | Reduce delivery delays by improving routing efficiency and visibility.
Success Criteria (measurable) | 10% reduction in late deliveries within 90 days; weekly ops dashboards adopted.
Key Stakeholders | Ops, IT, Finance
Renewal Date
Internal Notes (optional)
Use this space for discovery notes, risks, product context, or stakeholder dynamics.

## Onboarding Plan
Onboarding Plan (Outcome-Driven)
Onboarding Start |  |  | Target First Value Date |  |  | Time-to-Value (days)
Week | Milestone | Owner | Deliverable | Customer Outcome | Status | Due Date | Notes
1 | Kickoff + success alignment | CSM | Success plan v1 | Aligned outcomes & stakeholders | In progress
2 | Technical setup + access | Customer IT | SSO / permissions complete | Users can access core workflows | Not started
3 | Workflow configuration | CSM + Customer | Configured workflows | Ready to test scenarios | Not started
4 | Go-live + enablement | CSM | Training + playbook | Users complete key tasks | Not started
5 | First value review | CSM + Exec sponsor | Value check-in | First measurable impact confirmed | Not started

## Success Plan
Success Plan (Outcomes → Plays → Metrics)
Outcome | Metric | Baseline | Target | Owner | Due | Play / Approach | Status
Reduce late deliveries | % late deliveries | 12% | 10% | Customer Ops |  | Adoption of routing module + weekly ops review | In progress
Increase dashboard usage | Weekly active dashboard users | 15 | 30 | CSM |  | Enablement + stakeholder alignment | Not started
Improve visibility | # weekly ops reports shared | 1 | 3 | CSM |  | Executive-ready reporting cadence | Not started

## Health Model
Customer Health Model (simple, explainable)
Overall Health Score
Risk Level
Adoption %
How to read this model
This is a lightweight model designed for transparency. Use it as a signal, then add context via customer conversations and outcomes.
Driver | Weight | Score (0–100) | Notes
Adoption (core workflows) | 30% | 75 | Based on weekly active usage vs target
Value Realization | 25% | 65 | Outcome progress (success plan)
Stakeholder Engagement | 15% | 80 | Sponsor + team participation
Support Burden | 15% | 70 | Tickets/trends (lower is better)
Renewal Sentiment | 15% | 60 | Qualitative, validated in QBRs

## Exec Readout
Executive Snapshot (QBR-ready)
Account |  |  | Health |  | Risk
What changed since last review?
• Adoption increased in core workflow; early wins validated with Ops. • Sponsor engagement steady; next step is exec value review. • Support tickets trending down week over week.
Top Risks / Actions (next 30 days)
Risk | Impact | Mitigation / Next Action | Owner | Due
Executive sponsor bandwidth | Medium | Schedule 30-min value review; align to outcomes & metrics | CSM
IT backlog for integrations | High | Prioritize 1 integration tied to outcome; set milestone | Customer IT
La Toya Caldwell ¦ Customer Success & Tech Strategy